## Sheet1
# | File | Location | Priority | Phase 3 Area | Action Item | Status/Owner
1 | tokenService.ts | server/src/services/tokenService.ts | High | Backend Core | Fix corruption; restore token/consumeToken exports
2 | emailService.ts | server/src/services/emailService.ts | High | Backend Core | Implement sendVerificationEmail and sendResetPinEmail
3 | emailController.ts | server/src/controllers/emailController.ts | High | Backend Core | Fix imports after tokenService.ts repair
4 | versionRoutes.ts | server/src/routes/versionRoutes.ts | Low | Backend Cleanup | Remove placeholder or implement router
5 | metricsRoutes.ts | server/src/routes/metricsRoutes.ts | Low | Backend Cleanup | Remove placeholder or implement router
6 | receiptRoutes.ts | server/src/routes/receiptRoutes.ts | Low | Backend Cleanup | Remove placeholder or implement router
7 | metricsController.ts | server/src/controllers/metricsController.ts | Low | Backend Cleanup | Remove or implement handlers
8 | receiptController.ts | server/src/controllers/receiptController.ts | Low | Backend Cleanup | Remove or implement handlers
9 | versionController.ts | server/src/controllers/versionController.ts | Low | Backend Cleanup | Remove or implement handlers
10 | validateEnv.ts | server/src/config/validateEnv.ts | Medium | Backend Core | Implement env variable validation
11 | ocrService.ts | server/src/services/ocrService.ts | Low | Backend Cleanup | Remove until needed
12 | notificationService.ts | server/src/services/notificationService.ts | Low | Backend Cleanup | Remove until needed
13 | requestLogger.ts | server/src/middleware/requestLogger.ts | Low | Backend Cleanup | Remove until used
14 | rateLimit.ts | server/src/middleware/rateLimit.ts | Low | Backend Cleanup | Remove or wire via middleware
15 | cacheControl.ts | server/src/middleware/cacheControl.ts | Low | Backend Cleanup | Remove until used
16 | authGuard.ts | server/src/middleware/authGuard.ts | Low | Backend Cleanup | Remove until used
17 | sanitize.ts | server/src/utils/sanitize.ts | Low | Backend Cleanup | Remove or implement
18 | validation.ts | server/src/utils/validation.ts | Low | Backend Cleanup | Remove or implement
19 | migrate.ts | server/src/utils/migrate.ts | Low | Backend Cleanup | Remove or implement
20 | generate-client.ts | server/src/scripts/generate-client.ts | Low | Backend Cleanup | Remove or document
21 | logger.ts | server/src/utils/logger.ts | Medium | Backend Core | Ensure permissions; move logs to runtime path
22 | api.ts | frontend/src/services/api.ts | High | Frontend Runtime | Replace process.env with expo-constants or config
23 | config.ts | frontend/src/utils/config.ts | High | Frontend Runtime | Consolidate config source
24 | i18n/index.ts | frontend/src/i18n/index.ts | Medium | Frontend Runtime | Fix JSON import syntax
25 | tsconfig.json | frontend/tsconfig.json | Medium | Frontend Tooling | Add resolveJsonModule and Jest types
26 | Screen.tsx | frontend/src/components/layout/Screen.tsx | Medium | Frontend UI | Fix SVG import via react-native-svg
27 | bg-swirl.svg | frontend/public/images/bg-swirl.svg | Medium | Frontend Assets | Move to assets/images
28 | PinPad.tsx | frontend/src/components/ui/PinPad.tsx | Low | Frontend UI | Replace mask char with • or \u2022
29 | app.json | frontend/app.json | High | Frontend Config | Use Constants.expoConfig.extra.apiBaseUrl
30 | package.json | frontend/package.json | High | Frontend Config | Align Expo/RN versions
31 | package.json | frontend/package.json | Medium | Frontend Tooling | Add jest-expo or babel-jest preset
32 | tailwind.config.js | frontend/tailwind.config.js | Medium | Frontend Styling | Install nativewind or remove config
33 | styles/ | frontend/src/styles/**/*.css | Low | Frontend Styling | Remove or move to web package
34 | budgetStore.ts | frontend/src/store/budgetStore.ts | Medium | Frontend State | Rename to useBudgetStore
35 | investmentStore.ts | frontend/src/store/investmentStore.ts | Medium | Frontend State | Rename to useInvestmentStore
36 | uiStore.ts | frontend/src/store/uiStore.ts | Medium | Frontend State | Rename to useUiStore
37 | axiosAuthInterceptor.ts | frontend/src/middleware/axiosAuthInterceptor.ts | Medium | Frontend Networking | Implement and attach to API instance
38 | VerifyEmail/index.tsx | frontend/src/screens/VerifyEmail/index.tsx | Medium | Frontend Runtime | Use expo-linking for URL handling
39 | App.tsx | frontend/src/App.tsx | Medium | Frontend Navigation | Integrate react-navigation properly
40 | CleanTree.txt | Root | Low | Repo Cleanup | Remove from repo
41 | Sync-ToFinal.ps1 | Root | High | Repo Automation | Audit script; prevent leaks
42 | cli/ | cli/stable/_anchor.ps1, cli/quarantine/_anchor.ps1 | Low | Repo Cleanup | Remove or document purpose
43 | .github/workflows/ci.yml | .github/workflows/ci.yml | Medium | CI/CD | Add Jest config or skip frontend tests
44 | .editorconfig | Root | Low | Repo Standards | Normalize line endings; add pre-commit hook